## A - Risk Analysis
Risk analysis
Once risks have been identified, the risks are evaluated on a two dimensional matrix using a qualitative rating of the (i) impact of the risk and (ii) likelihood of the risk occurring to produce an overall level of risk indicator.
(i) Likelihood
Level | Descriptor | Description
1 | Rare | May occur in exceptional circumstances
2 | Unlikely | Could occur at some time
3 | Possible | Might occur at some time
4 | Likely | Will probably occur in most circumstances
5 | Almost certain | Is expected to occur in most circumstances
(ii) Impact
Level | Descriptor | Financial | Safety | Business activities | Social impacts | Reputation
1 | Insignificant | E.g. Less than $10,000 | No injuries | No disruption to the function | No social impacts | No significant adverse impact on organisation's reputation
2 | Minor | E.g. $10,001 - $100,000 | First aid treatment | Minimal disruption to the function | Minimal social impacts | Adverse impacts on the organisation's reputation
3 | Moderate | E.g $100,001 - $1M | Medical treatment | Significant disruption to the function | Significant social impacts | Direct adverse impact on the organisation's reputation
4 | Major | E.g $1M - $10M | Extensive injuries | Major disruption to the function | Major social impacts | Direct adverse impact on the organisation's reputation
5 | Catastrophic | E.g. Greater than $10M | Death | Severe disruption to the function | Severe ongoing impacts | Extensive damage to organisation's reputation
(iii) Overall level of risk
IMPACT
|  | Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5
LIKELIHOOD |  | 1 | 2 | 3 | 4 | 5
1 (rare) | 1 | Low | Low | Medium | High | High
2 (unlikely) | 2 | Low | Low | Medium | High | Extreme
3 (moderate) | 3 | Low | Medium | High | Extreme | Extreme
4 (likely) | 4 | Medium | High | High | Extreme | Extreme
5 (almost certain) | 5 | Medium | High | Extreme | Extreme | Extreme
Risks identified as extreme, and in some cases high, should be addressed immediately and a risk action plan completed. All risks should be assessed in terms of their priority and those with the highest priority should be addressed first, followed by lower priority risks.

## B - Risk Management Plan
RISK MANAGEMENT PLAN TEMPLATE
<EVENT NAME>
<DATE, VENUE>
NOTE: This template has been prepopulated with a range of samples. When preparing the risk management plan, consider all risks relevant to your event and assess the risk level, response and control measures as appropriate.
Step 1. Identify Risk |  |  | Responsibility |  | Step 2. Assess Risk without controls |  |  | Step 3. Control Measure | Step 4. Implement Controls | Step 4. Implement Controls | Step 5. Assess Risk
Num | Risk What can go wrong? | Consequences | Internal | External (Outside of Organisation) | Likelihood (1-5) | Impact (1-5) | Pre-control risk rating |  | Mitigation Plan Description What will we do to prevent it? | Mitigation Plan Description What will we do to prevent it? | Likelihood (1-5) | Impact (1-5) | Risk rating with controls | Action Plan What will we do if it happens? | Responsibility <insert title / name / initials>
1 | Administration | [12 empty] | Administration
A | Complaint made by general public in relation to an event. | Adverse publicity for <Organisation>. General public finds the event offensive and writes a letter to <Organisation>. | Event Coordinator | Venue, Suppliers and Contractors | 2 | 2 | Low | Administrative | - Complaint management process in place and communicated. - Ensure responses to potential complaints have been prepared in consultation with media agency / <Organisation> management. - Ensure clear communication to mitigate complaints from disappointment. - Event programming to be in line with objectives. - Adequate management and security in place at the Event | - Evaluate any potential causes for complaint and ensure adequate measures are in place to provide as much information to the public as possible. - Ensure responses to potential complaints have been prepared in consultation with PMU. - Event programming to be in line with Australia Day project plan - adequate management and security in place at the Event | 4 | 1 | Medium | - Collect all details of the complaint and ensure the complaint is dealt with, followed up and a response is issued, if required. - Record information in event report. | <Insert name, title or initials of responsible people>
| Low number of nominations received. | Insufficient nominations to judge or inappropriate nominations to award. | Event Coordinator |  | 2 | 2 | Low | Administrative | -Evaluate previous success rate and nomination numbers and develop a targeted marketing database. -Monitor nomination numbers in each category during the nominations period. -Review communication plan and implement new marketing activities as required. -Extend nomination period at discretion of Event Coordinators. |  | 2 | 3 | Medium | - Extend nomination period. - Implement new marketing techniques. - Request advice from judging panel for ideas on a way forward. - Encourage nominations through targeted marketing phone calls. | <Insert name, title or initials of responsible people>
C | Contracted performance group only has $5 million public liability insurance, not $20 million as requested. | If there is a large incident caused by the performance group, there may be a shortfall which the <Organisation> will be liable to pay. | Event Coordinator | Performers, Suppliers, Contractors | 3 | 4 | Extreme | Administrative | -Ensure the contractual agreement has the level of insurance required. |  | 1 | 3 | Medium | -Source options for one-off insurance coverage at the cost to either the contractor, or the organisation. -Request legal advise on how to proceed -Withhold payment | <Insert name, title or initials of responsible people>
2 | Planning and Approvals | [12 empty] | Planning and Approvals
B | E.g. Director / board / upper management change program or run order prior to event. |  |  |  | 2 | 5 | Extreme | [5 empty] | #N/A
F | E.g. Permit/s not approved. | [5 empty] | #N/A | [5 empty] | #N/A
3 | Programming and Production
I | E.g. Hazardous substances used on stage or during the event phase. (Examples: gas, helium, fire, pyrotechnics, CO2 blowers etc) | [5 empty] | #N/A | [5 empty] | #N/A
J | E.g. Patron or participant are injured during pre or post event production bump in or out process. | [5 empty] | #N/A | [5 empty] | #N/A
4 | Financial
| E.g. Budget overspend. | [5 empty] | #N/A | [5 empty] | #N/A
| E.g. Suppliers not paid on time. | [5 empty] | #N/A | [5 empty] | #N/A
| E.g. Sponsor fails to pay. | [5 empty] | #N/A | [5 empty] | #N/A
| E.g. Breach of contract - services. | [5 empty] | #N/A | [5 empty] | #N/A
5 | Public Relations and Marketing
| E.g. Misinformation published/distributed to attendees. | [5 empty] | #N/A | [5 empty] | #N/A
| E.g. Media not able to access event site. | [5 empty] | #N/A | [5 empty] | #N/A
| E.g. Negative media. | [5 empty] | #N/A | [5 empty] | #N/A
| E.g. Event website crashes. | [5 empty] | #N/A | [5 empty] | #N/A
6 | Human Resources
A | E.g. Key staff sick or has to take unplanned leave in lead up to project. | [5 empty] | #N/A | [5 empty] | #N/A
C | E.g. Available onsite staff / volunteers inexperienced. | [5 empty] | #N/A | [5 empty] | #N/A
D | E.g. Staff resources insufficient for size of project and project delivery is compromised. | [5 empty] | #N/A | [5 empty] | #N/A
E | E.g. Key event staff do not show due to illness etc. | [5 empty] | #N/A | [5 empty] | #N/A
F | E.g. External staff required onsite do not show up for their role. | [5 empty] | #N/A | [5 empty] | #N/A
7 | Communication
A | E.g. Failure to share pertinent information between stakeholders, venue and suppliers results in miscommunication. | [5 empty] | #N/A | [5 empty] | #N/A
D | E.g. Two way radios - handset and accessories fail. | [5 empty] | #N/A | [5 empty] | #N/A
8 | Environment and Climate
B | E.g. Inclement weather requiring event cancellation. Heavy rain or strong winds or extreme heat. | [5 empty] | #N/A | [5 empty] | #N/A
C | E.g. Damage caused to event site. | [5 empty] | #N/A | [5 empty] | #N/A
9 | Health and Safety
A | E.g Staff or contractors untrained or unskilled. | [5 empty] | #N/A | [5 empty] | #N/A
F | E.g A member of the general public is injured during the bump in or bump out phase. | [5 empty] | #N/A | [5 empty] | #N/A
10 | Entertainment and Programming
A | E.g Entertainment or artists not suited for intended audience. | [5 empty] | #N/A | [5 empty] | #N/A
C | E.g Master of Ceremonies (MC) late or unable to attend. | [5 empty] | #N/A | [5 empty] | #N/A
11 | Safety and Security
A | E.g Alcohol fuelled violence. | [5 empty] | #N/A | [5 empty] | #N/A
E | E.g Patrons do not adhere to evacuation. | [5 empty] | #N/A | [5 empty] | #N/A
12 | Crowd Management
B | E.g Patrons access stage or breach backstage areas. | [5 empty] | #N/A | [5 empty] | #N/A
C | E.g Inappropriate/inadequate barricades/fencing installed. | [5 empty] | #N/A | [5 empty] | #N/A
13 | Traffic and Transport
E | E.g Accident/incident involving vehicle movement inside within the event site. | [5 empty] | #N/A | [5 empty] | #N/A
F | E.g Closure of venue car park results in disruption. | [5 empty] | #N/A | [5 empty] | #N/A

## C - Approvals
Risk management plan
This risk assessment covers <Event name> delivered by the <Organisation> at <Venue> on <Date>.
Risk assessment compiled by: | <INSERT NAME>
Date: | <DATE>
Event: | <EVENT NAME>
Date of event: | <EVENT
Venue: | <EVENT VENUE>
Event assumptions: | All stakeholders to review this risk assessment to ascertain their responsibility and ability to implement treatment options.
All documents, plans, policies, procedures, staffing levels, training and support referred to and or required to ensure the treatments are effective as intended, will be in place.
All persons working to implement the proposed treatments will do so to the best of their ability and as well as can be reasonably expected.
Insert detail on any other assumptions
Event exclusions: | This risk assessment does not cover the risks associated with the following:
list any elements included in your event (for example: activation sites, media sites, markets, fireworks) that are not directly controlled or managed by your Events team (if any)
Risk Assessment reviewed by: | <INSERT NAME>
Date: | <DATE>
Risk level | Risk Description
EXTREME RISKS | <List overview of notable extreme risks here>
HIGH RISKS | <List overview of notable high risks here>
MEDIUM RISKS | <List overview of notable medium risks here>
LOW RISKS | <List overview of notable low risks here>

## Sheet1 (hidden)
B | Great Australian Bites Friday 24th January, 2014 from 5:00 to 21:30 hours. | Injury claim against Queensland Government. Negative publicity against the DPC. | EC | SBP | 3 | 3 | Medium | Administrative | Multicultural ticketed event for a nominated number of patrons (500) with Security provided for safety and security. BBQ cooking demonstrations in a relaxed dining experience. Strict adherence to RSA principles reducing the likelihood of Alcohol Fuelled Violence. | Multicultural ticketed event for a nominated number of patrons (500) with Security provided for safety and security. BBQ cooking demonstrations in a relaxed dining experience. Strict adherence to RSA principles reducing the likelihood of Alcohol Fuelled Violence. | 2 | 2 | Low | Defer to ABP Security protocols in relation to any incident or emergency at this location. | PC, EM | ü | ü | ü
C | Australia Day Festival at Southbank Sunday 26th from 10:00 to 19:30 hours. | Injury claim against Queensland Government. Negative publicity against the DPC. | EC | SBP | 3 | 3 | Medium | Administrative | Events Coordination, Department of Premier and Cabinet will partner with venues to provide a program of free entertainment including: - live music - art installations - creative shows and activities | Events Coordination, Department of Premier and Cabinet will partner with venues to provide a program of free entertainment including: - live music - art installations - creative shows and activities | 2 | 2 | Low | Defer to the SBP Security protocols in conjunction with the QPS contingent onsite. | PC, EM | ü | ü | ü
D | Flag Raising Ceremony Sunday 26th from 11:15 to 12:15 hours | Security Teams facilitating the Queensland Government personnel. Negative publicity against the DPC. | EC | ADF, QPS & SBP | 5 | 4 | High | Administrative & Engineering | Traditional flag raising ceremony - QPS to secure location and provide security with ABP staff. The ADF, Governor General, QLD Premier and other VIP's in attendance. | Traditional flag raising ceremony - QPS to secure location and provide security with ABP staff. The ADF, Governor General, QLD Premier and other VIP's in attendance. | 3 | 4 | High | Defer to SBP security protocols. QPS Security details to respond and take Forward Command of any credible threat against the event or a protected person. | PC, EM, DEC |  |  | ü
E | 21 Gun Salute Sunday 26th from 12:00 noon to 12:15 hours. | Injury claim against Queensland Government. Negative publicity against the DPC. | EC | ADF | 5 | 4 | High | Administrative & Engineering | Exclusion zones to be erected around gun firing area at Southbank. Only ADF personnel to operate within the exclusion zone. QWPS to maintain an exclusion zone on the Brisbane River. The EM, QPS and ADF to assemble together and maintain two way radio contact at all times to respond to any breaches of the zone or until the salute has been completed.. | Exclusion zones to be erected around gun firing area at Southbank. Only ADF personnel to operate within the exclusion zone. QWPS to maintain an exclusion zone on the Brisbane River. The EM, QPS and ADF to assemble together and maintain two way radio contact at all times to respond to any breaches of the zone or until the salute has been completed.. | 3 | 3 | Medium | In the case of a misfire, EC to follow instructions of ADF and EC. EC to liaise with traffic control management and maintain the exclusion zone. If suppliers / vendors cannot produce MSDS, the hazardous material to be removed from site. If injury occurs from a hazardous material, follow instructions listed on the MSDS. | PC, EM, DEC |  |  | ü
H | RAAF flypast featuring a FA18 hornet over the South Bank site. 12:00 noon sharp. | Injury from falling object. Noise complaints from unsuspecting persons. Injury claim against ADF and / or Queensland Govt. | EC | RAAF | 2 | 5 | Medium |  | The ADF will manage this process and lead any response to an incident in conjunction with SBP and QPS, | The ADF will manage this process and lead any response to an incident in conjunction with SBP and QPS, | 2 | 2 | Low | Public Address system updating patrons and the public of impending arrival of a jet over head. The ADF handing out ear plugs in the Cultural Forecourt area prior to the fly past. | PC, EM |  |  | ü
A | Adverse publicity for Queensland Government and financial loss to the department. | Promotional and financial liability to the state. | EC | SBP, Suppliers, QPS, ADF | 3 | 4 | Extreme | Administrative | GENERAL/PUBLIC - Follow processes during planning and onsite. - Volunteers required to sign a 'conditions of participation in event' form approved by CALS. - The Australia Day Festival is an all ages, alcohol free event is included on all pre-event signage and promotion. This is also included on all key Festival signage (tri-sigs) installed for the event day. | GENERAL - Ensure all processes are followed in the planning and delivery of event, and any issues are documented for debrief and post event review. All participating volunteers required to sign a 'conditions of participation in event' form approved by CALS. The Australia Day Festival is an all ages, alcohol free event' is included on all pre-event signage. This is also included on all key Festival signage (tri-sigs) installed for the event day. | 3 | 2 | Medium | Collect all details of the complaint and ensure the complaint is dealt with, followed up and a response is issued, if required. Record information in event report for post event review. | EM, DEC, MM | ü | ü | ü
[5 empty] | 3 | 4 | Extreme | Administrative | FLAG RAISING - A Deed of Indemnity is signed amongst the Commonwealth, State and the SBP to cover liability issues surrounding the gun salute and ceremony elements. | FLAG RAISING - A Deed of Indemnity is signed amongst the Commonwealth, State and the SBP to cover liability issues surrounding the gun salute and ceremony elements. | 3 | 2 | Medium | DPC to complete | DPC to complete |  |  | ü
[5 empty] | 3 | 4 | Extreme | Administrative | FESTIVAL Public Liability Insurance required and certificates of currency requested from entertainers and workshops. - SBP to provide online induction for EC staff. - SBP to ensure suppliers review and agree to Work Place Health and Safety manual before working on site. | FESTIVAL Public Liability Insurance required and certificates of currency requested from entertainers and workshops. - SBP to provide online induction for EC staff. - SBP to ensure suppliers review and agree to Work Place Health and Safety manual before working on site. | 3 | 1 | Medium | Refer any valid complaint to the appropriate department for further action. | EM, DEC | ü | ü
| Great Australian Bites | Friday 24 January 1700 hours to 2100 hours
1 x Stage
2 x dressing rooms ( 2 Pagodas)
Bar Marquee ( 39 m x 6 m )
VIP Bar
2 x small Bars
Food Stalls x 6 ( 3x3 structures )
MMM Activation
2 x 6 m x 3 m Portable Toilet Suites
1 Video Screen
Sirromet Tasting Activations
1 ATM
Food Demonstration Area
| Australia Day Festival | Sunday 26 January 2014 10:00 hours to 19:30 hours
Main Stage - Southbank Forecourt
Conservatorium Stage
Forest Green Stage
Courier mail Piazza - Area
Stage - Southbank Forecourt
VIP Marquee
VIP reception (Pagoda)
| Australia Day Flag Raising Ceremony | Sunday 26 January 2014 11:15 hours to 12:15 hours
Dias - Lectern, Flagpole, ADF band
VIP Marquee & seated area
VIP reception (Pagoda)
Guns for a 21 Gun Salute (ADF)
Temporary Fencing
Banana Bat Installation